## Slide 1
100+
MICROSOFT PARTNER OF THE YEAR 2023 · MODERN WORK LATAM
FIELD NOTES
I've delivered 100+ Microsoft 365 migrations across LATAM.
Here are the 5 lessons nobody tells you upfront.
→ Swipe
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
1/10

## Slide 2
WHY THIS MATTERS
The migration is the easy part.
What kills projects is everything that happens in the 90 days before and the 90 days after.
After 100+ projects — IMAP, Google Workspace, file servers, tenant-to-tenant — the same 5 mistakes show up every time.
Save this. Share with your team.
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
2/10

## Slide 3
LESSON 01
01
Discovery is not a checklist. It's a negotiation.
Half of “scope creep” is just discovery you skipped. Shared mailboxes nobody owns. Distribution lists tied to legacy apps. Public folders with 12 years of litigation evidence.
→ Spend 2x more time in discovery. You'll spend 5x less in remediation.
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
3/10

## Slide 4
LESSON 02
02
Identity comes first. Always. No exceptions.
If Entra ID isn't clean before you migrate mailboxes, you're moving broken accounts to a more expensive platform. Audit MFA coverage, conditional access baselines, hybrid sync health, and orphaned objects BEFORE the first mailbox moves.
→ No clean identity, no migration.
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
4/10

## Slide 5
LESSON 03
03
Pilot users are not random. They are political.
The wrong 50 pilot users will kill the rollout in week 2. Pick: 1 executive sponsor, 2 vocal skeptics, 5 power users from different departments, and 1 person from legal/compliance.
→ If the skeptics convert, the rest follow.
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
5/10

## Slide 6
LESSON 04
04
Communication beats tooling.
BitTitan, Quest On-Demand, native cutover — all of them work. What doesn't work: a 3-line email on Friday saying “your mailbox will move this weekend”. Build a comms cadence: T-30, T-14, T-7, T-1, day-of, T+1, T+7. Same template. Same channel. Every wave.
→ Predictability is the feature users buy.
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
6/10

## Slide 7
LESSON 05
05
The project ends 90 days after go-live, not on go-live.
Day 0 = mailbox moved. Day 90 = users actually changed behavior. Plan for: license rebalancing, DLP tuning, Conditional Access exceptions cleanup, OneDrive known folder move, adoption metrics review.
→ No post-migration plan = no ROI.
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
7/10

## Slide 8
THE PATTERN
The pattern behind all 5
✕
TEAMS THAT FAIL
Treat migration as a TECHNICAL project.
✓
TEAMS THAT SUCCEED
Treat it as a CHANGE project that happens to use technology.
The tools have been solved. The humans haven't.
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
8/10

## Slide 9
THE CHECKLIST
Before your next M365 migration, verify all 7:
Discovery doc signed by business owner
Entra ID baseline audit completed
Pilot user list with named individuals
Comms cadence template approved
Rollback plan documented and tested
Day +30 / +60 / +90 review scheduled
Success metrics defined in writing
Miss one → expect rework.
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
9/10

## Slide 10
LET'S CONNECT
I'm Fernando Olímpio.
Cloud & Security Consultant @ Avanade
Microsoft Partner of the Year 2023 — Modern Work, LATAM & Caribbean
I write weekly about Microsoft 365 Copilot adoption, secure migrations, and Modern Work.
→
Follow for more field notes
→
Repost to help your network
→
Comment which lesson hit hardest
Fernando Olímpio · linkedin.com/in/fernando-olímpio-da-silva
10/10